## District
DESIGN REVIEW COMMENT AND RESOLUTION FORM
| PROJECT NO.: | 607411
| DESCRIPTION: | Tisbury - Beach Road
| DESIGNER: | Greenman-Pedersen, Inc. |  | CONSULTANT EVALUATION SCORE: |  | 6 out of 10
| SUBMITTAL: | Revised 25% Design |  | DATE: | 2016-02-26
| REVIEW SECTION: | D5 Projects |  | REVIEWER NAME: | S. Serpa
| PROJ. MANAGER | Tom Currier
NO. | SHEET OR ITEM | COMMENT | INITIAL ACTION | RESPONSE | QC REVIEW INITIAL | FINAL ACTION VERIFIED
COMPLETED BY REVIEWER |  |  | COMPLETED BY DESIGNER |  |  | BY REVIEWER
Design Exception Report
1 |  | The Design Criteria Workbook incorrectly identifies Beach Road as a Non NHS roadway. Revise the report, workbook and Summary of Impacts to correctly identify the roadway as Other NHS and revise the request for lane and shoulder width exceptions to identify the minimum width requirements (12'/8') for this NHS (MAP 21) roadway. | A | This comment has been incorporated into the revised Design Exception Report. | CLS
2 |  | P.8 Design Criteria Workbook Summary Of Impacts The Minimum Alternative should be stated as having 5.5' sidewalks, not shoulders. | A | This comment has been incorporated into the revised Design Exception Report. | CLS
3 |  | On pages 2 and 7, it is not necessary to request formal design exceptions for the Shared Use Path's separation distance and width/shoulder elements, as these are not technically in the AASHTO Controlling Criteria. District Projects recommends breaking these out as separate paragraphs that ultimately document the approval of these design features by the MassDOT Complete Streets Engineer. | A | This comment has been incorporated into the revised Design Exception Report. | CLS
4 |  | On Sheet 14, before the end of the proposed sidewalk on the left side (Sta 24+40+), a label identifies the sidewalk as 4.5 feet wide, although it scales to be the same 5.5 feet as nearby standard-width sidewalk. If the narrowing of sidewalk below the 5.5 foot standard (including curb) is needed (due to the adjacent proposed retaining wall and ROW), include the substandard width in the DER, with the requisite justifications and impacts. E-14-006 requires a design exception for sidewalk less the standard width. Redraw the sidewalk to scale on plans, and add a note to the applicable Typical Section. | A | The note on Sheet 14 has been revised to read "PROP. 6.5' CEM. CONC. SIDEWALK", because the sidewalks have been widened by request. | JAT
5 |  | P.9 Design Criteria Workbook Summary Of Impacts Given the value of real estate on the island, the $2.75 M ROW cost for the major realignment seems quite low. Please justify basis of the cost and/or provide additional discussion in the narrative to document the ROW impacts. | A | The cost per square foot was estimated from an average of parcel values in the area. As noted the impacts to the buildings were not included. This would raise the cost substantially. | CLS
6 |  | P.9 Design Criteria Workbook Summary Of Impacts - Add Stopping Sight Distance to the Controlling Criteria line for Horizontal Alignment. | A | This comment has been incorporated into the revised Design Exception Report. | CLS
Pavement Design Checklist
7 | pg. 1 | Correct the functional classification identified for Beach Road. | A | This comment has been incorporated into the 75% Design Submission. | JAT
8 |  | Correct the recommended pavement structure to identify the Superpave Intermediate Course-19.0 (SIC 19.0) as included in the pavement notes. | A | The plans have been revised. SIC 19 is no longer proposed on this project. | JFO
General Comments
9 | 5 | HMA Walk is included in the Pavement Notes, but the item is not in the Estimate and no locations are identified on the Plans. District Projects recommends that for cost savings and maintenance purposes, the proposed cement concrete sidewalk and SUP be built with HMA throughout. The Pavement Note for the HMA Walk needs to be corrected to identify 1" Superpave Surface Course - 9.5 over 1-1/2" Superpave Intermediate Course -12.5. | A | The shared use path will be HMA and the plans have been revised accordingly. Through discussions with the project manager it was discussed to keep the sidewalks in the area from five corners to the beginning of the shared use path as cement concrete. At this point we would transistion to HMA for the SUP to the end of the project. | JAT
10 |  | Label the bearings, distances and curve data for the record baseline on the plans. | A | This comment has been incorporated into the 75% Design Submission. | JAT
11 |  | Provide a detail of the "Proposed Cement Concrete Retaining Wall with Steel Handrail" between STAs 23+00 to 23+93 LT with the next submission. | A | The design has been revised and a detail is included in the 75% Design Submission. | JFO
12 |  | Review the proposed crossings at WCR #8, 9 and 10, which do not provide a reciprocal ramp and direct pedestrians into a narrow shoulder. At a minimum, a reciprocal ramp or accessible landing area is required for all proposed crossings. | A | The Town would like to see crosswalks in these locations where there is no sidewalk across the street. We have provided accessible landing areas for these WCR's. | JAT
13 | 6, 14-16, 33 | Shared Use Path: In order to prevent a pronounced roller coaster effect along the SUP, we recommend using a sidewalk-through-driveway type that brings the sidewalk across the driveway without ramping down on either side. This will be most possible beginning Sta 26+40 (per the typical section), where the vegetated strip widens such that the vertical rise can be mitigated to avoid cars bottoming out on the driveway apron. Please review. Open to discussion at the CRM. | A | After discussions with the Town, project manager and complete streets engineer the following changes are proposed. From Sta. 20+50 (+/- the beginning of the SUP) to Sta. 25+50, the buffer has been increased to provide a 3' vegetated strip. This is accomplished by reducing the width of the SUP to 8' and taking an additional 0.5' of private property. The curb height has also been reduced to 4", this will allow for the driveway transitions to meet the sidewalk grade within the 3' buffer and not affect the elevation of the SUP. This will eliminate any roller coaster effect. | JAT
14 | 54-55 | The sections between STA 31+50 to 32+00 propose to match the existing cross slopes, which includes an abrupt change for a short segment. Review the feasibility of modifying the existing cross slopes at this location. | A | Full depth construction and typical 2.0% cross slopes are proposed throughout the project. | JFO
15 | 54-55 | The same cross sections also show a net pavement loss and abrupt shift of the crown. Full depth construction should be extended to Sta 32+50 | A | See above, full depth construction will be proposed throughout the project. | JAT
Comments By Plan Sheet
Typical Sections
P16 | 5 | Revise the pavement notes for the HMA Driveway to identify 1 1/2" Superpave Surface Course -9.5 (SSC 9.5). | A | This comment has been incorporated into the 75% Design Submission. | JAT
P17 | 5 | Correct the label on the right side of the Beach Rd section STA 15+00 to 17+68 to identify the edge treatment as loam and seed, not "Prop Walk". | A | This comment has been incorporated into the 75% Design Submission. | JAT
P18 | 5 | Correct the shoulder widths and right sidewalk labels on the Beach Rd section STA 19+28 to 20+53 to identify the variable shoulder and sidewalk/path widths as shown on the plans. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P19 | 6 | The Beach Rd section STA 22+14 to 24+40 incorrectly shows the shared use path within the existing SHLO limits. This section of the path is shown on the plans as beyond the existing layout limits and requires an alteration. Correct the layout labels on the right side accordingly and also correct the sidewalk width label on the left side to indicate the variable sidewalk width of 5.5' to 4.5' as shown on the plans. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P20 | 6 | The proposed pavement improvements shown on section STA 26+40 to 36+64 is not applicable for the length of this section. Provide a section for the proposed mill and overlay between STAs 31+00 and 36+64. This section should also identify the variable shoulder widths , cross slopes and alteration to the existing layout required on the right side for the proposed shared use path. | A | The limits of full depth reconstruction have been revised and incorporated into the typical sections. | JAT
Construction Plans & Profiles
P21 | 13 & 15 | The driveways at STAs 16+08 RT and 27+72 RT overlap property lines. Review the shared access at these locations. | A | The driveway at Sta. 16+08RT accesses two properties (#45 Tisbury Marina and #49 Vineyard Harbor Associates) #45 has rights to 20’ ROW (driveway) and #49 is parking for #60 Vineyard Harbor Condominium. The driveway design was revised to provide better separation with access to the property further east. The driveway at 27+72 appears to access parking for properties #151 & #159. There is no driveway easement unless it is shown on PB 299 PL 301 which is not available on line. | JFO
P22 | 13 | Identify the treatment of the "Conc Ret Wall", which is shown on the cross section as relocated curbing. | A | The Conc Ret Wall was mislabeled. It is a concrete paver wall that will be removed and rebuilt. | JAT
P23 | 16 | Correct the leader arrows for the labels on the left and right side at approximately STA 32+00 for the shared use path and temporary easement. | A | This comment has been incorporated into the 75% Design Submission. | JAT
Drainage & Utility Plans
P24 |  | District Projects prefers to locate CBs or GIs outside of a driveway opening. In some cases on this project, low points dictate that CB locations are within driveway openings. Please investigate the feasibility of altering profile/low points to address these particular CB locations. Open to discuss at the Comment Resolution Meeting (CRM). | A | All efforts have been made to minimize the amount of CBs located within a driveway opening. | JAT
P25 |  | Label the direction of flow for the existing drainage system. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P26 |  | Where there is inadequate cover over drainage pipes, use CL V RCP or Ductile Iron Pipe. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P27 |  | At the intersection to which the upgraded drainage system on Beach Rd. is directed at the western limit of the project, existing inverts are not complete. In addition, the drainage system along the Beach St. Extension should be included to depict the outlet location, per the PDDG. District Projects will be provide a plan of the existing drainage easement along this part of Beach St. Please update drainage plans accordingly. | A | The inverts have been completed and the drainage system has been updated. | JAT
P28 | 17 | Revise the proposed drainage between STAs 13+30 and 14+00 to address the following: - Adjust the DMH-104 location in order to provide room for a pair of CBs at the low point and a pair upstream on the flatter approach grade (up station). An additional DMH and trunk line adjustments required. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P29 | 18 | Approximately 150 ft. up station of the low point, a pair of existing CBs (14+98) are connected. As prescribed by the PDDG, eliminate the CB-CB conditions whenever possible; further, connecting them within the trunk line downstream to a low point CB is similarly not desirable. Please investigate alternatives to the drainage design to mitigate these issues. Open to discuss at the CRM. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P30 | 18 | Eliminate the CBCI-211. It is unnecessary in close proximity to the high point. | C | There will be a low point at this location created by the transition to superelevation around the curve. | CLS
P31 | 18 | Add CB to high side of WCR #4 and 10. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P32 | 19 | The plans identify the removal of the existing connection to the state drainage system, but proposes a swale to a leaching basin in close proximity to the gas pumps. Due to the high water table, it is doubtful that a LB will function properly. Please review to revise with an alternative drainage design for this location. Open to discuss at the CRM. | A | We have revised this area to include a 2.5' planting area behind the sidewalk. We have eliminated the swale and leaching basin, as well as the existing connection to the state drainage system. The District Permits section said they would notify the owner that the private drain connection must be removed. | JAT
P33 | 19 | Add low point catch basins at STA 21+21.76 as required by the PDDG. | C | This area is located in the runout/runoff portion of the superelevation and the structures are located at the low points. | CLS
P34 | 19 | Identify the existing CB at STA 25+04 LT as to be removed. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P35 | 19 | Label the existing SMH at STA 25+55 LT as to be adjusted. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P36 | 19 & 20 | Check the proposed location of CBCI-201, CBCI-311 and CB-308 for conflicts with the existing water main. | A | The existing water main has been proposed to be relocated in these areas. | JAT
P37 | 20 | Show the proposed location of CB-316 on the plan and revise the label to require a curb inlet. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P38 | 20, 21 | Drainage System - Sta 25+00+ to 31+00+ Determine if the existing 15"outlet at Sta 30+85+ Rt. will have adequate capacity to accommodate additional drainage proposed to be tied in. In addition, please investigate retaining the existing 12" RCP as a trunk line to the extent feasible. | A | The existing 15" outlet will have adequate capacity to accommodate the additional drainage. We investigated retaining the existing 12" RCP as a trunk line, however, we determined that it would not be practical. Trying to retain portions of the 12" RCP would cause manholes and CBs to be too close together and pipe angles not feasible. | JAT
P39 | 21 | Retain existing CB at Sta 35+50+ Lt. as a CIT to MH. Add a new CB adjacent in order to eliminate the CB-CB connection. | A | This comment has been incorporated into the 75% Design Submission. | JAT
Traffic Signs & Pavement Markings
P40 | 24 | Show the 405' of SWL between STAs 20+09 and 24+15 LT. | A | This comment has been incorporated into the 75% Design Submission. | JAT
Driveway Details
P41 | 33 | Detail on left side - Correct the designation of WCR #23 to be #24, and the offset to LT. instead of RT. Detail on right side - Correct the column heading: WCR # to be DWY #. | A | This comment has been incorporated into the 75% Design Submission. | JAT
Cross Sections
P42 |  | Critical cross sections alone are required at 25% design. The following comments are based on review of the cross sections provided. | N/A | No response necessary.
P43 | 35 | Add the location of the temporary easement on the left side of the section at STA 11+50 and show the limits of work for the brick sidewalk. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P44 | 37 | Add the HMA driveway apron to the right side of section at STA 13+50. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P45 | 38-43 | Please justify proposed full depth construction from Sta 15+00 to 18+00. The cross sections indicate either a fill condition or a match to the existing section. Also, it appears that full depth construction could be limited to the right lane/shoulder and leveling proposed for the left lane and shoulder between STAs 18+00 to 19+00. Review and revise limits of full depth construction. Identify a leveling course where necessary. | B | The depth of existing asphalt at B-1 (Sta. 14+30 +/-) is 8.5", at B-2 (Sta. 19+55 +/-). There is a reduction in pavement depth at some point between these two borings. Sta. 15+00 was chosen as a conservative alternative. However, after discussion with MassDOT, it has been determined to provide full depth construction throughout the entire project. | CLS
P46 | 38 | Correct the left side of section at STA 15+21 to show the limit of HMA driveway apron, gravel driveway and temporary easement line. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P47 | 40, 41, 49 | Add the location of the building to the sections at STAs 16+50 LT, 17+50 LT and 25+50 RT. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P48 | 42 | Correct the left side of section 18+50 to show the proposed limits of HMA driveway. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P49 | 44, 45 | Add the location of the temporary easement to the right side of sections at STAs 20+50, 21+00 and 21+13. Also, show the limits of HMA driveway on section 21+13 RT. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P50 | 46 | Correct the location of the temporary easement on the right side of section 22+50. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P51 | 47 | Add the existing stone wall/edging to the right side of the section at STA 23+00. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P52 | 47 | The driveway apron at STA 23+35 RT is shown extending beyond the limit shown on the construction plan and beyond the temporary easement. Correct the limits on the plan for consistency with the section and revise the location of the temporary easement as required. | A | The construction plans have been revised to show the correct driveway limit. | JAT
P53 | 48 | The driveway apron at STA 24+70 RT is not consistent with the limit shown on the plan. Revise plan for consistency. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P54 | 48-50 | The typical section notes for STAs 24+40 to 26+40 identify this segment of the project as in an area of transition, but the cross sections provided indicate proposed improvements similar to adjacent segments, full depth construction with a normal crown. Label the cross slopes on the sections within this segment or provide a typical section. | A | There is no transition between these stations. It is full depth construction with normal crown. The typical sections have been updated. | JAT
P55 | 49 | Add the existing stone wall to the section at STA 25+00 RT and correct the symbol for the proposed relocation of the stone wall. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P56 | 51, 55, 56, 58 | Add the location of the temporary easement to the right side of sections at STAs 27+76, 31+83, 32+00, 32+50, 33+00, 33+50, 34+00 and 36+00. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P57 | 52 | Add the limits of loam and seed to the right side of section at STA 28+50. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P58 | 53, 54 | Correct the location of the temporary easement on the left side of sections at STAs 29+00, 29+34, 29+50, 30+50, 31+00 and 31+50 for consistency with the construction plans. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P59 | 53, 54 | Extend the existing grade and add the limits of proposed walk/gravel to the sections at STAs 29+93 RT and 30+00 RT. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P60 | 54 | Correct the location of the permanent easement on the left side of section at STA 30+00 for consistency with the construction plans. | A | There is no longer a permanent easement required at this location. | JAT
P61 | 54 | Correct the limit of loam and seed/gravel on the right side of section at 31+50 and add the location of the temporary easement. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P62 | 56 | Add the location of the wall to the left side of sections at STAs 33+50 and 34+00. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P63 | 57 | Correct the limit of loam and seed on the left side of section at STA 34+50 for consistency with the plans. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P64 | 58 | Add the proposed shared use path limits to the section at STA 36+50 RT. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P65 | 58 | Add the location of the existing wall to the left side of sections at STAs 36+00, 36+50 and 36+64. | A | This comment has been incorporated into the 75% Design Submission. | JAT
Estimate
E66 |  | Item prices for projects on Martha's Vineyard should be increased 25-30% - to be reflected in the next submission. | A | This comment has been incorporated into the 75% Design Submission. | EMR
E67 |  | Add the Class A Trench Excavation item (141.) for the proposed retaining wall. | C | A wall is no longer being proposed, therefore, Class A Trench Excavation is no longer required. | EMR
E68 | 142. | Evaluate the need for Item 142. Class B Trench Excavation, based on the proposed drainage inverts. | A | Class B Trench has been kept as a contingency in the event it is needed. | EMR
E69 | 144. | The item for Class B Rock Excavation is not likely to be needed on this project. | A | Class B Rock Excavation has been removed from the estimate. | EMR
E70 |  | Add item 220.7-Sanitary Structure Adjusted to the estimate as necessary. | A | Item 220.7 has been added to the estimate. | EMR
E71 |  | Add item 767.12-Compost Filter Tubes as necessary for erosion control. | A | Item 767.12 has been added to the estimate | EMR
E72 | 691. & 706.1 | The unit prices for Items 691. and 706.1 appear low compared to the weighted average unit prices. Review and adjust as necessary. | A | This comment has been incorporated into the 75% Design Submission. | EMR

## ADA
DESIGN REVIEW COMMENT AND RESOLUTION FORM
| PROJECT NO.: | 607411
| DESCRIPTION: | TISBURY - BIKE & PEDESTRIAN IMPROVEMENTS ALONG BEACH ROAD, FROM THE TERMINATION OF THE EXISTING SHARED USE PATH WESTERLY TO THE FIVE CORNERS INTERSECTION
| DESIGNER: | Greenman-Pedersen, Inc. |  | CONSULTANT EVALUATION SCORE: |  | 5
| SUBMITTAL: | 25% REV |  | DATE: | 2016-01-13
| REVIEW SECTION: | HIGHWAY DESIGN - AAB/ADA |  | REVIEWER NAME: | LAUREL SENGER
| PROJ. MANAGER | Thomas Currier |  | APPROVED BY: | LOU RABITO
NO. | SHEET OR ITEM | COMMENT | INITIAL ACTION | RESPONSE | QC REVIEW INITIAL | FINAL ACTION VERIFIED
COMPLETED BY REVIEWER |  |  | COMPLETED BY DESIGNER |  |  | BY REVIEWER
P1 | PAGE #: 12-16 | Catch basin curb inlets (CBCI) may not be located adjacent to a ramp transition. For example, WCR #3 right transition. Please reconcile. | A | All catch basin curb inlets (CBCI) have been located outside of any ramp transitions. | JAT
P2 | PAGE #: 12-16 | Provide a level landing (at least 4 feet) between sidewalk transition sections. Please redesign. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P3 | PAGE #: 12-16 | Illustrate level landing/turning space grade breaks at the top of all perpendicular curb ramps on Construction Plan sheets. Refer to MassDOT Construction Standard, E107.3.0. For example, WCR #3, 5, 8, 9 and 10. | A | WCRs #3&5 have been revised. WCRs #8-10 use the shared use path as the level landing, so there will be no grade breaks shown on the plan. | JAT
P4 | PAGE #: 12-16 | There is a grade break missing from DWY #22. Please review all curb ramps for proper illustration of grade breaks. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P5 | PAGE #: 12-16 | What's happening between Sta. 24+40 through 26+40 and between Sta. 29+10 through 36+64 project limits? If applicable, please provide grade breaks which are in line with MassDOT Construction Standards. | A | Between WCR #6 and Sta 36+00 the curb reveal will be 4". This allows the driveway transition to meet the path elevation without requiring grade breaks. | CLS
P6 | PAGE #: 14 | DWY #29 is not a MassDOT Construction Standard. Consider ending the sidewalk with WCR #6 (right transition would no longer be necessary). Otherwise, consider using MassDOT Construction Standard, E107.6.0, to terminate the sidewalk at the driveway. | A | The proposed cem. conc. sidewalk will end adjacent to the driveway and the driveway apron material shall be HMA. The town requested ADA access to this property via the driveway as is currently used by cruise tourists. | JFO
P7 |  | The back edge of the parallel or parallel/perpendicular curb ramps (CR) or driveway sidewalk transition sections will have diverging surfaces in the plane of the adjoining sidewalks, walkways, business entrances, stairway platforms, etc. when the CR/driveway back edge does not coincide with the back edge of the sidewalk or pedestrian path of travel. Please redesign or recommend applying for a variance. (multiple locations - including, but not limited to, the brick walk removed and relaid) | B | We believe this has been addressed. Please specify locations if this has not been been properly addressed. | JAT
P8 |  | Fixed objects (i.e. utility poles, hydrants, signs, signal foundations, etc.) shall not be placed in any part of the curb ramp. Please reconcile. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P9 |  | Please confirm that an unobstructed 3'-0" path of travel, excluding curb, shall be maintained past any obstruction. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P10 | PAGE #: 32 | Curb ramp transition ramp running slopes may not exceed 7.5%*. Please review and revise WCR #1, 2, 3 and 8. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P11 | PAGE #: 32-33 | The next submission should include schedules for both driveway aprons with continuous sidewalk and wheelchair ramps, if proposed, which are cross-referenced with the plans. The schedules should include the referenced roadway baselines, station and offset to the center of the opening at the gutter line, gutter profile slope, opening width at the gutter, left transition length, right transition length, depth from the gutter to the back of the sidewalk, and the depth of the level landing or width of path of travel across driveways. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P12 | PAGE #: 32-33 | Please provide +/- signs for the roadway gutter slope direction in the curb ramp tables. Also, provide an explanatory diagram of the direction of the gutter slopes. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P13 | PAGE #: 32-33 | Please provide curb ramp construction details with a sectional view for all the types of wheelchair ramps and driveway aprons with continuous sidewalk crossings, if proposed. All proposed construction plans with WCR’s and DWY’s must use those outlines that comply with the types of curb ramp construction details provided by MassDOT Construction Standards. The selected scaled symbols used for the construction plans must be reflective of the finished ramp or driveway apron. Please provide a sectional view for Sidewalk through Driveway with Landscaping. | A | This comment has been incorporated into the 75% Design Submission. | JAT
O1 |  | The AAB requires when construction upgrades one curb ramp of an intersection crossing, a reciprocal curb ramp is also provided and compliant. If the reciprocal curb ramp already exists, the designer is required to verify for the project manager that the reciprocal curb ramp is compliant (a basic report for the project records). If the reciprocal curb ramp is not compliant, regardless of the project boundaries, the curb ramp is required to be brought into compliance. | C | This comment would require geometric improvements to all five approaches. The intersection is constricted and would require apex WCR's on the Beach St approach. There are also existing catch basin structures located at the entrance to the WCRs that are not ideal and may require relocation. Additionally, there would appear to be a need for additional takings/easements to complete the work. After further discussion and providing the District with 2 options, it was agreed upon to cut the project short of the intersection in order to not redesign the entire five corners intersection. | JAT
O2 |  | ALL COMMENTS WITH OR WITHOUT EXAMPLES ARE NOT INTENDED TO BE INCLUSIVE, BUT APPLY TO THE ENTIRE PROJECT AND THE ENTIRE PROJECT SHOULD BE REVIEWED TO COMPLY WITH EACH COMMENT. IN ADDITION, THE ENTIRE PROJECT SHOULD BE REVIEWED FOR OTHER AAB/ADA COMPLIANCY ISSUES NOT FOUND.

## Traffic D5
DESIGN REVIEW COMMENT AND RESOLUTION FORM
| PROJECT NO.: | 607411
| DESCRIPTION: | Tisbury-Beach Road
| DESIGNER: | Greenman-Pedersen, Inc. |  | CONSULTANT EVALUATION SCORE:
| SUBMITTAL: | 25% Revised |  | DATE: | 2016-02-02
| REVIEW SECTION: | D5-Traffic |  | REVIEWER NAME: | Keri A. Gallagher
| PROJ. MANAGER | Tom Currier
NO. | SHEET OR ITEM | COMMENT | INITIAL ACTION | RESPONSE | QC REVIEW INITIAL | FINAL ACTION VERIFIED
COMPLETED BY REVIEWER |  |  | COMPLETED BY DESIGNER |  |  | BY REVIEWER
1 | 23 | STA. 19+70 WB - R3-17 & R3-17a signs (bike lane AHEAD), consider placing these signs ahead of the bike lane | A | The R3-17a [AHEAD] plaque is confusing because the bike lane begins at this location and have been removed. R3-17/R3-17a sign assembly has been installed in advance at Sta. 20+60 LT. | TQN
2 | 23 | STA. 19+00 EB - consider a separate curb cut for bikes entering the shared use path, instead of having bikes use the WCR. | A | Due to limited right of way and close proximity of the driveway, the proposed shared used path (SUP) cannot be extended to Sta. 19+00 EB and have a separate curb cut for bikes. However, the ramp opening at Sta. 20+00 has been extended (widened) in each direction to provide better maneuvering for an eastbound bike to enter the SUP. | TQN
3 | 23 | STA. 20+15 WB consider tapering the SWEL from the 2 foot shoulder to the 4 foot shoulder | A | This SWL was deleted by mistake. It has been added. | TQN
4 | 24 | STA. 24+15 to 20+09 - correct the SWEL to show a 2 foot shoulder | A | This SWL was deleted by mistake. It has been added. | TQN
5 | 23-24 | STA. 20+00 - this crosswalk is on a curve. Have sight distances been checked for the posted speed limit? | A | Yes. The sight distance of 200' have been checked for the posted speed limit design speed of 30 MPH. FYI, sight distance easement has been proposed on both sides of the WCR to achieve required 200' sight distance. | TQN
6 | 23-26 | Crosswalks - advanced warning signs are needed for all crosswalks | A | In accordance to the MUTCD, advanced crosswalk warning signs W11-2/W16-9p are optional. In order not to clutter the sidewalk and especially the shared used path with signs, the crosswalk located on the curved segment shall have the optional advanced warning signs. One additional advanced warning sign is proposed on the westbound approach to the project limits (Sta. 38+25±LT) | TQN
7 | 25-26 | Crosswalks @ STA. 29+21, 31+17, & 35+74 are missing WCR on the northern side | A | The Town would like to see crosswalks in these locations where there is no sidewalk across the street. We have provided accessible landing areas for these WCR's. | TQN
8 | 25-26 | Are the above mentioned crosswalks justified? | A | These are existing crosswalk locations. | TQN
9 | 26 | STA. 32+20 LT - remove the leader with prop. Bike Lane Marking (TYP.) | A | This typographical error has been deleted. | TQN

## Traffic Boston
COMMENT AND RESOLUTION FORM
| PROJECT NO.: | 607411
| DESCRIPTION: | Tisbury: Bicycle and Pedestrian Improvements along Beach Road
| DESIGNER: | GPI |  | CONSULTANT EVALUATION SCORE: |  | 7.5
| SUBMITTAL: | 25% |  | DATE: | 2016-04-11
| REVIEW SECTION: | Boston HQ Traffic Engineering |  | REVIEWER NAME: | Syed Akhtar
| PROJ. MANAGER | Thomas Currier, P.E.
NO. | SHEET OR ITEM | COMMENT | INITIAL ACTION | RESPONSE | QC REVIEW INITIAL | FINAL ACTION VERIFIED
COMPLETED BY REVIEWER |  |  | COMPLETED BY DESIGNER |  |  | BY REVIEWER
1 | FDR P9 | Why have 2013 crash data not been used in the FDR? Crash data of 2013 are available on the MassDOT webpage. Were crash data also collected from local Police Department for comparison? | A | It is unclear why the 2013 crash data was not used at the time the original FDR was prepared and submitted (May 2015). Local crash data was collected from 2009-2011. The crash data and memo has been provided with this submission. | JFO
2 | FDR P15 | Fix the typo Table 3, not Table 4 under the Construction Management Outline. | A | Comment noted | JFO
3 | FDR General Note | Why have there been no safety concerns/details added to the FDR from the Road Safety Audit conducted on March 17, 2015 prior to this submission? | B | The RSA safety concerns for the Beach Road approach have been addressed in the current design. Improvements at the intersection are not within the scope of the current project. The limit of work has been discussed with the project manager. | JFO
4 | Plan 1 | Please use the updated file which is now available on the MassDOT CAD Standard webpage to have the correct text for controlling documents on the Title Sheet and Index. Reference to The 1996 Construction and Traffic Standard Details has been removed from the update. | A | The controlling documents reference has been updated. | JFO
5 | Plan 22-23 | Consider using a modified plaque R3-17cP "BEGIN" in place of R3-17a "AHEAD" at Sta.10+90RT and Sta.19+70LT. | A | This comment has been incorporated into the 75% Design Submission. | TQN
6 | Plan 22-26 | Per MassDOT Preference, recommend using ladder type crosswalks for this project. | B | The Town is in the process of considering the use of bituminous street prints as an option for these crosswalks. They will be discussed with District Maintenance after the 75% Submission to ensure the requests are within the scope of District resources to maintain. | TQN
7 | Plan 23 | Speed limit sign at Sta.16+50LT is being discarded but not replaced. Please review. | B | After further review, the speed limit sign at Sta. 16+50 LT does not correpond with Special Speed Regulation No. 683 and therefore it has not been replaced. FYI, a speed limit R2-1(20) sign is proposed at Sta. 11+80 LT to match the regulation. | TQN
8 | Plan 23-26 | Has consideration been given to add advance warning signs for CW's? | A | Yes. Due to the location of these crosswalks, sight distance is not a problem as motorists will be able to see the warning signs at the crosswalks. | TQN
9 | Plan 24 | Speed limit sign at Sta.21+25RT is being discarded but not replaced. Please review. | B | FYI, a speed limit R2-1(30) sign is proposed at Sta. 11+45 RT to indicate the beginning of a 30 MPH speed zone in corresponding with Special Speed Regulation No. 683. In order not to clutter the roadway with signs, speed limit sign at sta. 21+25 RT will not be replaced. | TQN
10 | Plan 24 | SWL 405' long is missing from Sta. 20+10LT to Sta. 24+15LT | A | This comment has been incorporated into the 75% Design Submission. | TQN
11 | Plan 27 | To ease the mounting procedure, the street name sign will be printed on one side (POS), and two street name signs for the same street will be mounted together on one post. | A | This comment has been incorporated into the 75% Design Submission. | TQN
12 | Plan 27 | To ease the fabrication, the designer will need to specify the width of the street name sign. | A | The sign has been designed with Sign CAD and the width has been provided in the Sign Summary. | TQN
13 | Plan 28 | For pedestrian safety, use updated version of Type I Pedestrian Bypass. The updated version is circled on the attached sheet. | A | The latest version of the Pedestrian Bypass has been incorporated into the 75% Design Plans. | JAT
14 | Plan 30 | Background Sheeting for all construction warning signs shall be of a fluorescent orange color. Refer to Section 850 MassDOT Supplemental Specifications dated July 1, 2015. Revise the plan accordingly. | A | The Construction Sign Summary has been revised to read Fluorescent Orange as the Background sheeting. | JAT

## Complete Streets
DESIGN REVIEW COMMENT AND RESOLUTION FORM
| PROJECT NO.: | 607411
| DESCRIPTION: | Tisbury - Beach Road
| DESIGNER: | GPI |  | CONSULTANT EVALUATION SCORE: |  | 5
| SUBMITTAL: | 25% Design Submission Revised |  | DATE: | 2016-02-01
| REVIEW SECTION: | Complete Streets Engineer (CSE) |  | REVIEWER NAME: | Luciano Rabito, P.E.
| PROJ. MANAGER | Thomas Currier
NO. | SHEET OR ITEM | COMMENT | INITIAL ACTION | RESPONSE | QC REVIEW INITIAL | FINAL ACTION VERIFIED
COMPLETED BY REVIEWER |  |  | COMPLETED BY DESIGNER |  |  | BY REVIEWER
1 | General | The plans show two 4.5' bike lanes and two sidewalks for the first segment. For the second, there is a a sidepath varying in width from 8' to 10' with a variable offset to the roadway. The second sidewalk terminates before the end of the project. This is the cross section that was agreed upon by the District, Town , Designer and CSE. Therefore, it is acceptable. | A | Noted. | CLS

## Environmental
DESIGN REVIEW COMMENT AND RESOLUTION FORM
| PROJECT NO.: | 607411
| DESCRIPTION: | Tisbury- Beach Road
| DESIGNER: | GPI |  | CONSULTANT EVALUATION SCORE: |  | 6
| SUBMITTAL: | 25% Resubmission- APPROVED |  | DATE: | 2016-01-20
| REVIEW SECTION: | Environmental |  | REVIEWER NAME: | Mark Kolonoski
| PROJ. MANAGER | Tom Currier
NO. | SHEET OR ITEM | COMMENT | INITIAL ACTION | RESPONSE | QC REVIEW INITIAL | FINAL ACTION VERIFIED
COMPLETED BY REVIEWER |  |  | COMPLETED BY DESIGNER |  |  | BY REVIEWER
1 | GEN | The Designer has provided appropriate evidence of early environmental coordination. The DE is asked to forward any response to Environmental Services- Attn: Mark Kolonoski upon receipt. | A | All responses will be forwarded.
2 | GEN | The response to EEC Checklist Item 10 (Wetland Resource Areas) indicates that the project is within 100' of a salt marsh. However, the revised 25% plans, which include a 9/24/15 deliniation by Nover-Armstrong, do not include the identification of salt marsh. The DE is aked to verify whether or not salt marsh is located within or direcly adjacent to the project area. | B | The salt marsh was identified on MassGIS "Oliver" mapping. It does not appear to be within the project limits. | CLS
3 | GEN | The DE submitted a draft CE with the original 25% design. The DE is asked to provide an updated project description with details regarding the multi-use path. This description can be provided as a stand alone document and does not need to be inserted onto the CE template. The description can be forwarded to Mark.Kolonoski@dot.state.ma.us. | A | A revised CE Checklist will be provided with the 75% Submittal. | JFO
4 | GEN | The EEC indicates that the project will require permitting with the ACOE pursuant to Section 404 of the Clean Water Act. However, work in water is not shown on the 25% redesign submission. The DE is asked to provide clarification regarding this matter. | A | It is our understanding that because the entire project is within "Barrier Beach" and there are impacts to "Dune" areas then the project is subject to permitting under section 404 of the Clean Water Act. Please advise if this is not the case. | JFO
5 | GEN | If the project does involve WIW, it will requrie a CZM consistency letter; even if an ENF is not requried. A draft CZM consistency letter should be included in the 75% design submission if deemed necessary. | A | A draft CZM consistency letter will be submitted with the Draft NOI submission. | JFO
6 | GEN | The entire project is located within FEMA designated flood zone AE. Given the installation of the sidewalk north of Beach Rd, which is currently vegetated, there is reason to believe the project may result in a loss of flood storage. The DE is aked to to verify whether or not there will be a loos of flood storage and, if so, identify a compensation area on the 75% design submission. | A | The sidewalk width will gradually be decreased from 6.5 ft to 5.5 ft after the driveway at Sta 21+00 LT and down to 4.5 ft around Sta 23+00 LT until it meets the driveway at Sta 24+40 LT. The purpose for this is to reduce any loss of flood storage. We are providing dune restoration in the beach area as desired by CZM. | JFO
7 | GEN | The project will require the filing of a NOI with the Tisbury Conservation Commission. A draft NOI must be submitted to MassDOT no later than with the 75% design. The 75% design submission will not be considered complete without a draft NOI. | A | A draft NOI will be submitted to MassDOT for review shortly following the 75% Design submittal. | JFO
8 | GEN | The project is currently being reviewd by MassDOT's Stormwater Unit. Any comments or concerns will be sent to the PM in the coming weeks. | N/A | No response necessary
9 | GEN | The project will require a Section 106 effect finding issued by MassDOT's Cultural Resources Unit. CRU is currently reviewing the design and will provide the PM with any comments or concerns in the coming weeks. | N/A | No response necessary

## FHWA (hidden)
DESIGN REVIEW COMMENT AND RESOLUTION FORM
PROJECT NO.:
DESCRIPTION:
| DESIGNER: |  |  | CONSULTANT EVALUATION SCORE:
| SUBMITTAL: |  |  | DATE:
| REVIEW SECTION: |  |  | REVIEWER NAME:
PROJ. MANAGER
NO. | SHEET OR ITEM | COMMENT | INITIAL ACTION | RESPONSE | QC REVIEW INITIAL | FINAL ACTION VERIFIED
COMPLETED BY REVIEWER |  |  | COMPLETED BY DESIGNER |  |  | BY REVIEWER

## DUCE
DESIGN REVIEW COMMENT AND RESOLUTION FORM
| PROJECT NO.: | 607411
| DESCRIPTION: | Tisbury - Bike & Pedestrian Improvements along Beach Road
| DESIGNER: | Greenman-Pedersen, Inc. |  | CONSULTANT EVALUATION SCORE: |  | 6
| SUBMITTAL: | REV25% |  | DATE: | 2016-03-24
| REVIEW SECTION: | District 5 - DUCE |  | REVIEWER NAME: | Chris Betourney / RFB
| PROJ. MANAGER | Thomas H. Currier
NO. | SHEET OR ITEM | COMMENT | INITIAL ACTION | RESPONSE | QC REVIEW INITIAL | FINAL ACTION VERIFIED
COMPLETED BY REVIEWER |  |  | COMPLETED BY DESIGNER |  |  | BY REVIEWER
O1 |  | Utilities currently identified within the project limits have been noted on the attached REV25% Project Utility Summary sheet. In accordance with Engineering Directive E-11-008, private utility owners are eligible for 50% and municipal utility owners are eligible for 100% cost reimbursement for required relocations. A detailed scope of work and an itemized estimate of costs will be required from the affected utilities. This scope and estimate will be provided to the State Utilities Engineer. | A | Utility Coordination is underway.
O2 |  | There are service risers requiring relocation on this project. All private secondary electric service risers on utility poles to be relocated will need to be identified, and Item 826.7 Electric Service Riser Relocation added as a separate contract Item. | A | Item 826.70 has been included in the estimate and the relocations have been identified. | EMR
Typical Sections
P3 | 5 | For the micro milled Typical Section Sta. 10+42 to Sta. 15+00, the proposed cross slopes shown on the Cross Sections are variable across the sections and inconsistent in between stations. Recommend changing the proposed cross slope from "meet existing" to 2.0%. | A | The cross slopes have been revised. However, it should be noted that the project is now all full depth construction. | JAT
P4 | 6 | The Typical Section for Sta. 26+40 to Sta. 36+64 shows full depth construction, however the cross sections indicates mill and overlay between Sta. 31+50 and Sta. 36+64. Please reconcile. | A | This typical section has been revised and another section has been added to reflect the actual design. | JAT
Drainage & Utility Plans
P5 | 12 thru 21 | Please add the missing pole riser and street light information to the base plan pole labels. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P6 | 12 thru 21 | Per the meeting held on 2/5/2016, all UP's being R&R are to be set 1ft behind the proposed sidewalk and 3ft behind the shared-use path. Also, the Town requested that all OHW services crossing the roadway be replaced with underground services to existing/proposed manholes, HH's and/or service poles. The relocation of the services underground will be non-participating. To be discussed at the upcoming DUCE Utility Field Meeting. | A | This comment has been incorporated into the 75% Design Submission. The underground services will be discussed with the Town of Tisbury. | JAT
P7 | 12 thru 21 | Change the labels for the existing water main from: 12" DI to: 12" DI Water. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P8 | 12 thru 21 | Please change the labels for the existing sewer main from: 2" HDPE to: 2" HDPE FM Sewer, and from: 3" HDPE to: 3" HDPE FM Sewer. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P9 | 12 thru 21 | There are possible vertical conflicts with the existing 3" and 2" HDPE sewer lines that cross the proposed drainage lines. Provide all sewer manhole inverts and adjust any proposed drainage lines as needed. Contact the Tisbury DPW and obtain the missing information. | A | A full drainage design has been provided for the 75% submission and all existing inverts are now shown on the plans. | JAT
P10 | 12 thru 21 | Label existing drainage pipes being abandoned within the proposed full depth areas as "REM". | A | This comment has been incorporated into the 75% Design Submission. | JAT
P11 | 12 thru 21 | Show a dashed line around the outer perimeter of each proposed catch basin and manhole as shown on Exhibit 18-10, PPDG; in order to identify utility conflicts. Additionally, where proposed drainage structures are in close proximity to existing underground utilities, offset structures should be shown and labeled. (See Attached Detail) | A | This comment has been incorporated into the 75% Design Submission. | JAT
P12 | 12 thru 21 | Provide a Drainage Structure Data Table which incudes' the structure #, type, station, rim elevation, inverts in/out and remarks columns in the table. (Refer to the sample drainage table in MassDOT's 2006 Project Development & Design Guide, chapter 18, page 20) | A | This comment has been incorporated into the 75% Design Submission. | JAT
P13 | 12 thru 21 | There are multiple structures within the project limits labelled as "OMH". Please identify the utility that these manholes are associated with and show their underground facilities on the base plans in the next submission. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P14 | 18 | Per the meeting held on 2/5/2016, the Town requested that all obstructions be located outside of the proposed sidewalks and SUP. As a result, relocate the existing hydrant at Sta.15+91RT behind the proposed sidewalk with it's required WM Easement | A | This comment has been incorporated into the 75% Design Submission. | JAT
P15 | 19 & 20 | Show and label a tide gate in proposed DMH#200 at Sta.21+49LT and CIT#301 at Sta.30+82RT in order to prevent backflow into the proposed drainage system. | A | This comment has been incorporated into the 75% Design Submission. | JAT |  | How do we show one? I just labeled it
P16 | 19 & 20 | Include a label to "ADJ" the existing SMH at Sta.25+55LT. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P17 | 20 | The existing private LP at Sta.26+93LT will conflict with the proposed OHW relocations. Please label this LP to be R&R (BO). This will need to be addressed during the ROW process. | A | The proposed utility pole locations have been relocated across the roadway. The exisitng LP will not be affected by the OHW. | JAT
P18 | 20 | Graphically show the proposed CB#313 at Sta.28+68RT on the plans. (See Comment # P11) | A | This comment has been incorporated into the 75% Design Submission. | JAT
P19 | 20 & 21 | Per the email sent on 02/24/2016, please note that the increase in width of the buffer strip from: 1.5ft to: 3ft will place the existing hydrant at Sta.26+63RT within the shared-use path. Please show and label this hydrant being R&R behind the shared-use path, 3ft from the center of the hydrant to the back of the proposed path, along with its required WM easement. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P20 | 20 & 21 | The distance between the relocated OHW's and existing fuel tanks at Sta. 30+00LT do not meet the required clearances needed by Eversource-Electric. As a result, it is recommended that the OHW's be relocated underground from relocated UP#131/26 to existing UP#131/29. To be discussed at the upcoming DUCE Utility Field Meeting. | A | The proposed utility pole locations have been relocated across the roadway avoiding clearance issues near the existing fuel tanks. An underground service is proposed between UP #131/28 and UP #131/33. | JAT
Traffic Sign & Pavement Markings
P21 | 22 thru 26 | Per the meeting held on 2/5/2016, the Town requested that all obstructions be located outside of the proposed sidewalks and SUP. As a result, locate traffic signs behind the sidewalk, wherever a 5.5' sidewalk is proposed adjacent to the roadway, to allow for required ADA/AAB clearances. (Refer to 2009 MUTCD, Sect. 2A.16, Figure 2A-2, C-Roadside Sign In Business Commercial Or Residential Area.) Where the SUP is proposed the signs should be placed in the buffer strip a minimum 2ft from the face of curb. | A | This comment has been incorporated into the 75% Design Submission. | JAT
Temporary Traffic Control Plan
P22 | 29 | Remove the Two Lane Road Shoulder And Travel Lane Closed detail. The existing roadway's width will not allow for this type of traffic setup. | A | The proposed road will be 30ft wide from station 10+32 to 20+50. There would be a possibility of shoulder/sidewalk work where this scheme could be utilized. We can delete in the next submission if desired. | JFO
P23 | 29 | Include the Full Depth Construction - Construction Not In Progress detail with the next submission. (See Attached Detail) | A | This comment has been incorporated into the 75% Design Submission. | JAT
Construction Details
P24 | 31 | In the Hydrant Installation Hydrant Removed And Reset detail please change the label for the new hydrant from: Hydrant To Be Adjusted To Grade As Required, Rotate As Necessary to: Hydrant's Bottom Flange To Be Set 2-4" From Finished Grade And Rotated As Necessary. | A | This comment has been incorporated into the 75% Design Submission. | JAT
P25 | 31 | Please include a leaching basin detail for the proposed LB at Sta.20+49LT. (See Attached Detail) | C | This is not necessary since we are not proposing a leaching basin anymore. | JAT
P26 | 31 | Include an offset catch basin detail. (See Comment # P11) & (See Attached Detail) | A | This comment has been incorporated into the 75% Design Submission. | JAT
P27 | 31 | Please provide a plan and profile of the proposed retaining wall from Sta.22+97LT to Sta.23+92LT, which includes the top and bottom of wall elevations. | C | The proposed retaining wall has been removed from the plans. | JAT
Cross Sections
P28 | 54 thru 58 | The left side cross slope for the cross sections from Sta. 31+50 to Sta. 35+00 is sloped toward the roadway's center line not the edge of road, correct the direction of cross slope arrow. Also, the typical section shows full depth construction not mill and overlay in this area, please reconcile. (See comments # P3 & P4) | A | The pavement treatment has been revised to full depth construction throughout the project limits. | JAT
Estimate
E29 | 129.5 | Include Item 129.5 - Track Excavation to the estimate to address the removal of the existing marine railway within the SHLO at Sta.29+00LT & RT. | A | Item 129.5 has been added to the estimate. | EMR
E30 | 141 | Include Item 141 - Class A Trench Excavation to the estimate for the proposed retaining wall from Sta.22+97LT to Sta.23+914LT. | C | A wall is no longer being proposed, therefore, Class A Trench Excavation is no longer required. | EMR
E31 | 151.2 | Include Item 151.2 - Gravel Borrow For Backfilling Structures And Pipes referenced in note #2 in the Drainage Trench Detail in the Construction Details. | C | The note has been updated to no longer reflect item 151.2. | EMR
E32 | 156 | Recommend increasing the quantity of Item 156 - Crushed Stone for the proposed drainage work due to the high water table in this area. | A | This comment has been incorporated into the 75% Design Submission. | EMR
E33 | 220.5 | Remove Item 220.5 - Drainage Structure Remodeled from the estimate. There are no drainage structures proposed to be remodeled on this project. | A | Item 220.5 has been removed from the estimate. | EMR
E34 | 220.7 | Include Item 220.7 - Sanitary Structure Adjusted to the estimate for the (3) SMH's proposed to be ADJ. (See Comment # P16) | A | Item 220.7 has been added to the estimate. | EMR
E35 | 227.1 | Include Item 227.1 - Tide Gate. The existing 18" and 15" outlet pipes for the drainage system are currently below sea level and will require a back flow preventer. (See Comment # P15) | A | Item 227.1 has been added to the estimate. | EMR
E36 | 303.06 | Include Item 303.06 - 6 Inch Ductile Iron Water Pipe (Mechanical Joint) to the estimate for the hydrants being R&R. (See Comments # P14 & P19) | A | Item 303.06 has been added to the estimate. | EMR
E37 | 303.12 | Remove Item 303.12 - 12 Inch Ductile Iron Water Pipe (Mechanical Joint) from the estimate. There are no proposed water relocations on this project. | C | There are now proposed water main relocations requiring item 303.12. | EMR
E38 | 350.08 | Remove Item 350.08 - 8 Inch Gate and Gate Box from the estimate. There are no 8" water pipes on this project. | A | Item 350.08 has been removed from the estimate. | EMR
E39 | 376.2 | Include Item 376.2 - Hydrant Removed And Reset to the estimate. (See Comments # P14 & P19) | A | Item 376.2 has been added to the estimate. | EMR
E40 | 660 | Please include Item 660 - Metal Pipe Rail to the estimate for the proposed handrail from Sta.22+97LT to Sta.23+914LT. | C | Metal Pipe Rail is no longer being proposed as part of this project. | EMR
E41 | 823.71 | Include Item 823.71- Highway Lighting Pole and Luminaire Removed and Stacked along with its required special provision as a contingency for a private LP that is not R&R by the owner in a timely manner. (See Comment # P17) | A | Item 823.71 has been added to the estimate. | EMR
E42 | 856 | Please include Item 856 - Arrow Board shown in the Two Lane Road Shoulder Closed detail in the Temporary Traffic Control Plan. | A | Item 856. has been added to the estimate. | EMR
E43 | 996.01 991.1 | Include Item 996.01 - Wall Structure, Wall No.1 for the proposed retaining wall from Sta.22+97LT to Sta.23+914LT, along with its companion Item 991.1 - Control Of Water - Structure No.1. | C | The proposed retaining wall has been removed from the plans. | JAT

## DER Comments
COMMENT AND RESOLUTION FORM
| PROJECT NO.: | 607411
| DESCRIPTION: | Tisbury - Beach Road
| DESIGNER: | Greenman-Pedersen, Inc. |  | CONSULTANT EVALUATION SCORE: | N/A
| SUBMITTAL: | Revised Design Exception Report (dated March 2016) |  | DATE: | 2016-05-24
| REVIEW SECTION: | D5 Projects |  | REVIEWER NAME: | S. Serpa
| PROJ. MANAGER | Tom Currier
NO. | SHEET OR ITEM | COMMENT | INITIAL ACTION | RESPONSE | QC REVIEW INITIAL | FINAL ACTION VERIFIED
COMPLETED BY REVIEWER |  |  | COMPLETED BY DESIGNER |  |  | BY REVIEWER
Previous Comments not Adequately Addressed
1 |  | Revise the Design Exception Report, workbook and summary of impacts to correctly identify the minimum lane (12') and shoulder (8') width requirements for this NHS roadway. | A | This comment was incorporated into the revised Design Exception Report submitted on May 26th. | CLS
3 |  | Revise the controlling criteria summary paragraph on page 6 to remove the reference to the shared use path width and separation distance design exceptions. These design elements do not require a formal design exception. | A | This comment was incorporated into the revised Design Exception Report submitted on May 26th. | CLS
New Comment
|  | Section 4.2, Additional Design Criteria Not Met, of the report requests design exceptions for both shared use path width and separation. These criteria do not require a formal design exception request as previously noted. Revise the report to document that the proposed design does not meet the minimum guidelines in the PDDG and have been developed in coordination with MassDOT and the Town of Tisbury. Also, the minimum shared use path width for this project is noted as 8' and the minimum separation as 3', which is not consistent with the 9' width and 1.5' separation proposed on the revised 25% submission. Revise report as necessary. | A | This comment was incorporated into the revised Design Exception Report submitted on May 26th. | CLS

## Pavement
DESIGN REVIEW COMMENT AND RESOLUTION FORM
| PROJECT NO.: | 607411
| DESCRIPTION: | Tisbury Beach Road
| DESIGNER: | GPI
| SUBMITTAL: | 25 |  | DATE: | 2016-11-02
| REVIEW SECTION: | MassDOT Pavement Management Section |  | REVIEWER NAME: | K. FitzGerald
| PROJ. MANAGER | T. Curry
NO. | SHEET OR ITEM | COMMENT | INITIAL ACTION | RESPONSE | QC REVIEW INITIAL | FINAL ACTION VERIFIED
COMPLETED BY REVIEWER |  |  | COMPLETED BY DESIGNER |  |  | BY REVIEWER
|  | The proposed project indicates 4 out of 5 cores with 7-10 inches of HMA and one outlier with 4 inches of HMA. The pavement cores appear to be older sheet mixes or sand mixes. The pavement scope of work indicates approximately 1000 feet of mill and overlay and 1600 feet of full depth construction. The Design Engineer is recommended to increase the full depth construction to the limits of work rather than mobilize milling operation for 1,000 feet. Removing old HMA sheet mixes will provide a more consistent pavement section with better performance, service life and simpler construction operation. THe full depth construction will reduce small box widenings and cement concrete base course and allow better compaction of roadway materials. The SN for the pavement above the sub-base is 2.5 for a twenty year design. The pavement section to satisfy this is 6.5 inches of HMA. The SN for a 40 year design is 2.7 and the pavement section to satisfy this is 7.5 inches. Revising the full depth pavement to 7.5 inches should cost to enable more full depth construction. The pavement section is suggested as follows: | A | Full depth construction will be provided throughout the entire project limits. | JAT
|  | Proposed Pavement Notes Proposed Full Depth Constuction 1.5" Superpave Surface Course 9.5 (SSC-9.5) over Asphalt Emulsion for Tack Coat over 2" Superpave Intermediate Course 12.5 (SIC-12.5) over Asphalt Emulsion for Tack Coat over 4" Superpave Base Course 37.5 (SBC-37.5) over 4" Dense Graded Crushed Stone for Sub-base over 8" Gravel Borrow Type b or existing suitable sub-base compacted Prop HMA Drives 1.5" Superpave Surface Course 9.5 (SSC-9.5) over Asphalt Emulsion for Tack Coat over 2" Superpave Intermediate Course 12.5 (SIC-12.5) over 8" Gravel Borrow Type b or existing suitable sub-base compacted Prop HMA Walks 1" Superpave Surface Course 9.5 (SSC-9.5) over Asphalt Emulsion for Tack Coat over 1.5" Superpave Intermediate Course 12.5 (SIC-12.5) over 8" Gravel Borrow Type b or existing suitable sub-base compacted | A | This comment has been incorporated into the 75% Design Submission. | JAT
|  | Full Depth Construction will provide better grade controls at back of sidewalk and better traffic management. Old pavement 7-10 inches thick may be able to be removed and repaved with fine grading and compacting and new 7.5-inch HMA pavement. | A | Noted. | JAT

## HazMat
COMMENT AND RESOLUTION FORM
| PROJECT NO.: | 607411
| DESCRIPTION: | Tisbury - Bike & Pedestrian Improvements Along Beach road, From the Termination of the Existing Shared Use Path Westerly to the Five Corners Intersection
| DESIGNER: | Greenman-Pedersen, Inc. |  | CONSULTANT EVALUATION SCORE: |  | 5
| SUBMITTAL: | 25% |  | DATE: | 2017-01-03
| REVIEW SECTION: | Environmental - Hazmat |  | REVIEWER NAME: | Katherin McArthur
| PROJ. MANAGER | Thomas H. Currier
NO. | SHEET OR ITEM | COMMENT | INITIAL ACTION | RESPONSE | QC REVIEW INITIAL | FINAL ACTION VERIFIED
COMPLETED BY REVIEWER |  |  | COMPLETED BY DESIGNER |  |  | BY REVIEWER
1 |  | A review of the Massachusetts Department of Environmental Protection (DEP) sites list for releases of oil and hazardous materials (OHM) revealed a number of listed sites. To assess the potential to encounter contamination from these sites, a file review was performed. Based on the information obtained during the DEP file review, RTN 4-1136, RTN 4-11082, RTN 4-12524, RTN 4-13294, RTN 4-14290, RTN 4-17249, and RTN 4-17583 may environmentally impact the soil and groundwater within the project area. Please see the uploaded summary of potentially impacting releases and HASP recommendations for details. It is recommended that the summary be included in the Special Provisions package so that the HASP will be properly implemented and executed in the areas where OHM contamination will likely be encountered. | A | Noted. | JAT

## Blank
DESIGN REVIEW COMMENT AND RESOLUTION FORM
PROJECT NO.:
DESCRIPTION:
| DESIGNER: |  |  | CONSULTANT EVALUATION SCORE:
| SUBMITTAL: |  |  | DATE:
| REVIEW SECTION: |  |  | REVIEWER NAME:
PROJ. MANAGER
NO. | SHEET OR ITEM | COMMENT | INITIAL ACTION | RESPONSE | QC REVIEW INITIAL | FINAL ACTION VERIFIED
COMPLETED BY REVIEWER |  |  | COMPLETED BY DESIGNER |  |  | BY REVIEWER